## Sheet1
SC Smart Safe Cities - CM Tehsils Project (Bahawalpur Division)
Activity ID | Activity Name | Original Duration | Start | Finish
SC Smart Safe Cities - CM Tehsils Project (Bahawalpur Division) |  | 4 | 2026-01-19 | 2026-01-22
SC.1 Project Milestone |  | 1 | 2026-01-19 | 2026-01-19
A1000 | Start Date | 0 | 2026-01-19
A1010 | Compeletion Date | 0 |  | 2026-01-19
SC.2 Bahawalpur Division |  | 4 | 2026-01-19 | 2026-01-22
SC.2.1 Bahawalnagar |  | 4 | 2026-01-19 | 2026-01-22
SC.2.1.1 Chishtian |  | 4 | 2026-01-19 | 2026-01-22
SC.2.1.1.1 Camera & Field Surveillance System |  | 4 | 2026-01-19 | 2026-01-22
SC.2.1.1.1.1 Camera Poles & Foundations |  | 4 | 2026-01-19 | 2026-01-22
A1020 | Survey & Marking | 4 | 2026-01-19 | 2026-01-22
A1030 | Excavation | 4 | 2026-01-19 | 2026-01-22
A1040 | PCC | 4 | 2026-01-19 | 2026-01-22
A1050 | Foundation Concrete | 4 | 2026-01-19 | 2026-01-22
A1060 | Curing & Backfilling | 4 | 2026-01-19 | 2026-01-22
A1070 | Pole Erection | 4 | 2026-01-19 | 2026-01-22
SC.2.1.1.1.2 ANPR Poles & Foundations |  | 4 | 2026-01-19 | 2026-01-22
A1080 | Excavation & Foundation | 4 | 2026-01-19 | 2026-01-22
A1090 | Pole Installation | 4 | 2026-01-19 | 2026-01-22
SC.2.1.1.1.3 Power Cabinets for Camera & ANPR |  | 4 | 2026-01-19 | 2026-01-22
A1100 | Cabinet Foundation | 4 | 2026-01-19 | 2026-01-22
A1110 | Cabinet Installation | 4 | 2026-01-19 | 2026-01-22
A1120 | Internal Wiring | 4 | 2026-01-19 | 2026-01-22
SC.2.1.1.1.4 Camera Installation |  | 4 | 2026-01-19 | 2026-01-22
A1130 | Fixed Camera Installation | 4 | 2026-01-19 | 2026-01-22
A1140 | PTZ Camera Installation | 4 | 2026-01-19 | 2026-01-22
A1150 | ANPR Camera Installation | 4 | 2026-01-19 | 2026-01-22
A1160 | Strobe Light Installation | 4 | 2026-01-19 | 2026-01-22
SC.2.1.1.1.5 Body Worn Camera System |  | 4 | 2026-01-19 | 2026-01-22
A1170 | Body Cameras Deployment | 4 | 2026-01-19 | 2026-01-22
A1180 | Dock & Storage Setup | 4 | 2026-01-19 | 2026-01-22
SC.2.1.1.1.6 Field Devices |  | 4 | 2026-01-19 | 2026-01-22
A1240 | Panic Button Installation | 4 | 2026-01-19 | 2026-01-22
A1250 | Attendance Device Installation | 4 | 2026-01-19 | 2026-01-22
SC.2.1.1.1.7 Field Equipment Configuration |  | 4 | 2026-01-19 | 2026-01-22
A1190 | Camera Addressing & Labeling | 4 | 2026-01-19 | 2026-01-22
A1200 | Initial Camera Testing | 4 | 2026-01-19 | 2026-01-22
SC.2.1.1.2 Power & Electrical Infrastructure |  | 4 | 2026-01-19 | 2026-01-22
SC.2.1.1.2.1 Power Supply Works |  | 4 | 2026-01-19 | 2026-01-22
A1260 | Power Cable Laying | 4 | 2026-01-19 | 2026-01-22
A1270 | Panel Installation | 4 | 2026-01-19 | 2026-01-22
A1280 | Earthing & Grounding | 4 | 2026-01-19 | 2026-01-22
SC.2.1.1.2.2 Backup Power Systems |  | 4 | 2026-01-19 | 2026-01-22
A1290 | UPS Installation | 4 | 2026-01-19 | 2026-01-22
A1300 | Battery Installation | 4 | 2026-01-19 | 2026-01-22
A1310 | Generator Installation | 4 | 2026-01-19 | 2026-01-22
A1320 | Generator Testing & Commissioning | 4 | 2026-01-19 | 2026-01-22
SC.2.1.1.2.3 Split AC Installation |  | 4 | 2026-01-19 | 2026-01-22
A1330 | AC Mounting | 4 | 2026-01-19 | 2026-01-22
A1340 | Electrical Connections | 4 | 2026-01-19 | 2026-01-22
A1350 | Testing | 4 | 2026-01-19 | 2026-01-22
SC.2.1.1.3 OFC, Network & Connectivity |  | 4 | 2026-01-19 | 2026-01-22
SC.2.1.1.3.1 OFC Route Survey & Design |  | 4 | 2026-01-19 | 2026-01-22
A1360 | Route Survey | 4 | 2026-01-19 | 2026-01-22
A1370 | Design Approval | 4 | 2026-01-19 | 2026-01-22
SC.2.1.1.3.2 OFC Civil Works |  | 4 | 2026-01-19 | 2026-01-22
A1380 | Trenching | 4 | 2026-01-19 | 2026-01-22
A1390 | Duct / Pipe Laying | 4 | 2026-01-19 | 2026-01-22
A1400 | Manhole Construction | 4 | 2026-01-19 | 2026-01-22
A1410 | Backfilling & Restoration | 4 | 2026-01-19 | 2026-01-22
SC.2.1.1.3.3 OFC Installation |  | 4 | 2026-01-19 | 2026-01-22
A1420 | OFC Cable Pulling | 4 | 2026-01-19 | 2026-01-22
A1430 | Splicing | 4 | 2026-01-19 | 2026-01-22
A1440 | OFC Testing | 4 | 2026-01-19 | 2026-01-22
SC.2.1.1.3.4 Aerial GPON OFC |  | 4 | 2026-01-19 | 2026-01-22
A1450 | Pole Installation | 4 | 2026-01-19 | 2026-01-22
A1460 | Aerial OFC Laying | 4 | 2026-01-19 | 2026-01-22
A1470 | Termination & Testing | 4 | 2026-01-19 | 2026-01-22
SC.2.1.1.3.5 Network Connectivity |  | 4 | 2026-01-19 | 2026-01-22
A1480 | ISP Coordination | 4 | 2026-01-19 | 2026-01-22
A1490 | Site Connectivity Setup | 4 | 2026-01-19 | 2026-01-22
A1500 | Bandwidth Testing | 4 | 2026-01-19 | 2026-01-22
SC.2.1.1.4 Control Room Development |  | 4 | 2026-01-19 | 2026-01-22
SC.2.1.1.4.1 Control Room Civil Works |  | 4 | 2026-01-19 | 2026-01-22
A1510 | Renovation Works | 4 | 2026-01-19 | 2026-01-22
A1520 | Flooring & Ceiling | 4 | 2026-01-19 | 2026-01-22
A1530 | Painting & Finishing | 4 | 2026-01-19 | 2026-01-22
SC.2.1.1.4.2 Furniture & Fixtures |  | 4 | 2026-01-19 | 2026-01-22
A1540 | Workstations Installation | 4 | 2026-01-19 | 2026-01-22
A1550 | Chairs Installation | 4 | 2026-01-19 | 2026-01-22
SC.2.1.1.4.3 Network Equipment |  | 4 | 2026-01-19 | 2026-01-22
A1560 | Core Switch Installation | 4 | 2026-01-19 | 2026-01-22
A1570 | Network Switch Installation | 4 | 2026-01-19 | 2026-01-22
A1580 | Firewall Installation | 4 | 2026-01-19 | 2026-01-22
SC.2.1.1.4.4 Display Systems |  | 4 | 2026-01-19 | 2026-01-22
A1590 | Video Wall Installation | 4 | 2026-01-19 | 2026-01-22
A1600 | Monitoring Screen Installation | 4 | 2026-01-19 | 2026-01-22
SC.2.1.1.5 IT Systems, Servers & Software |  | 4 | 2026-01-19 | 2026-01-22
SC.2.1.1.5.1 Server & Storage Systems |  | 4 | 2026-01-19 | 2026-01-22
A1610 | SAN Storage Installation | 4 | 2026-01-19 | 2026-01-22
A1620 | HDD Installation | 4 | 2026-01-19 | 2026-01-22
A1630 | GPU Server Installation | 4 | 2026-01-19 | 2026-01-22
SC.2.1.1.5.2 VMS & AI Systems |  | 4 | 2026-01-19 | 2026-01-22
A1640 | VMS Installation | 4 | 2026-01-19 | 2026-01-22
A1650 | AI NVR Configuration | 4 | 2026-01-19 | 2026-01-22
A1660 | Analytics Configuration | 4 | 2026-01-19 | 2026-01-22
SC.2.1.1.5.3 Software & Applications |  | 4 | 2026-01-19 | 2026-01-22
A1670 | PSCA HQ Integration | 4 | 2026-01-19 | 2026-01-22
A1680 | Mobile Application Deployment | 4 | 2026-01-19 | 2026-01-22
A1690 | Digital Twin Customization | 4 | 2026-01-19 | 2026-01-22
SC.2.1.1.5.4 System Licensing |  | 4 | 2026-01-19 | 2026-01-22
A1700 | Camera Licenses | 4 | 2026-01-19 | 2026-01-22
A1710 | System Licenses | 4 | 2026-01-19 | 2026-01-22
SC.2.1.2 Fort Abbas |  | 0
SC.2.1.3 Haroon Abad |  | 0
SC.2.1.4 Minchinabad |  | 0
SC.2.2 Bahawalpur |  | 0
SC.2.2.1 Ahmadpur East |  | 0
SC.2.2.2 Hasilpur |  | 0
SC.2.2.3 Khairpur Tamewali |  | 0
SC.2.2.4 Yazman |  | 0
SC.2.3 Rahim Yar Khan |  | 0
SC.2.3.1 Khanpur |  | 0
SC.2.3.2 Liaquatpur |  | 0
SC.2.3.3 Sadiqabad |  | 0